## FS_Defect_Report
Project Name - Fashion Store mobile Application
Document Name - Defect Report
Created By - Tishany.T
Date - 14.04.2026
|  | Module | Defect Title | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported By | Reported Date | Remarks
FS_DEF_01 | FS_TC_04 | Login | Password visibility toggle not working | Password visibility icon does not show or hide password text on login screen | 1.Open login screen 2.Enter password 3.Click visibility icon | Password should toggle between visible and hidden | No change in password visibility | Low | Medium | closed | Tishany T. | 14-Apr-2026 | Fixed and retested successfully
FS_DEF_02 | FS_TC_16 | Cart | Cart item deletion not working | User is unable to remove items from the shopping cart | 1.Add item to cart 2.Navigate to cart 3.Click delete/remove icon | Selected item should be removed from cart | Item remains in cart | High | High | closed | Tishany T. | 14-Apr-2026 | Item removal works after fix
FS_DEF_03 | FS_TC_15 | Cart | Update cart quantity not working | Increasing or decreasing product quantity does not update cart | 1.Add item to cart 2.Change quantity 3.Observe update | Cart quantity should update correctly | Quantity remains unchanged | High | High | closed | Tishany T. | 14-Apr-2026 | Cart quantity updating after fix
FS_DEF_04 | FS_TC_19 | Checkout | Cart not cleared after successful order | After placing order, cart items are not removed | 1.Add items to cart 2.Place order 3.Return to cart | Cart should be empty after order placement | Items remain in cart | Medium | High | Open | Tishany T. | 14-Apr-2026 | Issue still reproducible
FS_DEF_05 | FS_TC_23 | Profile | Profile image not loading | Profile image fails to load or display in user profile | 1.Open profile screen 2.Check profile picture | Profile image should load correctly | Image not displayed | Medium | Medium | Open | Tishany T. | 14-Apr-2026 | Profile image still not updating